## Sheet1
New Ways to Play: A Study in Alternative Game Controllers |  |  |  |  | Date: 03/11/2025
TASK |  | Phase |  | Start Date |  | Duration (weeks) |  | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01
Find Components to build Controller |  | Research Phase |  | 2025-11-03 |  | 2
Game Engine |  | Research Phase |  | 2025-11-17 |  | 2
Resource Plan |  | Research Phase |  | 2025-12-01 |  | 2
Research Project |  | Research Phase |  | 2025-12-15 |  | 2
Assemble Controller |  | Technical Implementation Phase |  | 2025-12-29 |  | 2
Code Controller |  | Technical Implementation Phase |  | 2026-01-12 |  | 2
Unity Setup |  | Technical Implementation Phase |  | 2026-01-26 |  | 2
Development of Controller and Game |  | Technical Implementation Phase |  | 2026-02-09 |  | 2
Game Design |  | Gameplay Design Phase |  | 2026-02-23 |  | 2
Code Check |  | Gameplay Design Phase |  | 2026-03-09 |  | 2
User Interface |  | Gameplay Design Phase |  | 2026-03-23 |  | 2
Final Version of Controller and Case / Unity Game |  | Gameplay Design Phase |  | 2026-04-06 |  | 2
Gather Participants |  | Completion Phase |  | 2026-04-20 |  | 1
Optimized and Calibrated |  | Completion Phase |  | 2026-04-27 |  | 1
Internal Testing |  | Completion Phase |  | 2026-05-01 |  | 1
Complete Project |  | Completion Phase |  | 2026-05-05 |  | 1
| Research Phase |  | Technical Implementation Phase |  |  |  | Gameplay Design Phase |  |  |  | Completion Phase